## Sheet1
Task | Effort(person-days) | Duration(days) | Dependencies
A: Requirement gathering | 2 | 2
B: Tasks analysis | 1 | 1 | A
C: Feasibility study | 2 | 2 | A
D: purchase hardwares and set room | 4 | 2 | B,C
E: User Interface design | 10 | 5 | B,C
F: User Interface design implementation | 6 | 3 | D, E
G: Feature Implementation | 4 | 2 | D,E
H: Define users | 2 | 2 | D,E
I: Test and Debug | 8 | 8 | F,G